## Project Overview
Project Tracker v0.1 |  | Instructions: |  |  |  | Finds task with the most urgency/importance from Action Items.
|  | Modify 'Project Name (WAM)' and 'Task Name (WAM)' accordingly. The other cells will update automatically based on content in the Action Items tab. Add new rows when you get new projects. | [6 empty] | Inspired by the Eisenhower Matrix:
By: Austin Owens | [5 empty] | 0 = most 9 = least
Project Name (WAM) | Task Name (WAM) | Total Action Items | Open | In Progress | Closed | Urgency | Importance | Estimated Hrs Left
Project A | Task A | 3 | 3 | 0 | 0 | 1 | 0 | 18
Project B | Task B | 1 | 0 | 1 | 0 | 6 | 6 | 10
Project B | Task C | 1 | 1 | 0 | 0 | 5 | 3 | 20
Project C | Task D | 1 | 0 | 0 | 1 | N/A | N/A | 0

## Action Items
Action Items |  | Instructions: |  | Ugency' over 'Importance' Multiplier: | 5 |  |  |  | Color Code: > =30 days: Green <=29 days: Yellow < =14 days: Orange <=5 days: Red
|  | Update/add information accordingly. 'Project Name (WAM)' and 'Task Name (WAM)' columns update their dropdown options based on what you put in the 'Project Overview' tab. 'Task Order column' uses algorithm to determine what your task order should be based on Urgency and Importance columns. Filter your task order from smallest to largest to see your task order. |  |  |  | o | o = open
Don't modify, only filter/sort/hide. |  |  |  | 0 = most 9 = least |  | i | i = in progress
[6 empty] | c | c = closed
Task Order | Project Name (WAM) | Task Name (WAM) | Action Item | Urgency 0-9 | Importance 0-9 | Status o/i/c | Estimated Hrs | Entry Date | Due Date | Last Updated | Notes | Links
1.4 | Project A | Task A | Prepare for PDR | 1 | 2 | o | 5 | 2022-02-08 | 2022-03-15 | 2022-02-26 | Something I need to remember
4.4 | Project A | Task A | Perform board bring-up on new hardware | 3 | 7 | o | 10 | 2022-01-02 | 2022-03-05 | 2022-02-26 | Something I need to remember
5.6 | Project B | Task C | Write software to enable thing 1 | 5 | 3 | o | 20 | 2022-01-18 | 2022-01-18 | 2022-02-26 | Something I need to remember
7 | Project A | Task A | Always find time for the things that make you feel happy to be alive | 7 | 0 | o | 3 | 2022-01-01 | 2022-06-07 | 2022-02-26
7.2 | Project B | Task B | Write software to do other thing | 6 | 6 | i | 10 | 2022-02-04 | 2022-06-01 | 2022-02-26
99 | Project C | Task D | Implement Rust on more embedded hardware | 8 | 4 | c | 40 | 2010-07-07 | 2022-10-10 | 2022-02-26

## Metadata
Unique Project Name | Unique Task Name
Project A | Task A | DON’T MESS WITH THIS TAB UNLESS YOU KNOW WHAT YOUR DOING
Project B | Task B | This tab is used throughout the excel spreadsheet for data
Project C | Task C | validation of cells within the Action Items tab.
Task D